## Project Management Plan
PROJECT: Build a CI/CD pipeline
| Week | Tasks | Backend | Frontend | Local | Demo
Q1 CI (Build system) App development | 2020-10-01 | Build system | Setup virtual environment
| 2020-10-08 |  |  |  |  | Monday morning demo
| 2020-10-15 |  | Write makefile
| 2020-10-22 |  |  |  |  | Monday morning demo
| 2020-10-29 |  | Create virtual environment
| 2020-11-05 |  |  |  |  | Monday morning demo
| 2020-11-12 | ML API | Create prototype for local prediction
| 2020-11-19 |  |  |  |  | Monday morning demo
| 2020-11-26 |  |  |  | Create dockerfile
| 2020-12-03 |  |  |  |  | Monday morning demo
| 2020-12-10 |  | Create ML microservice
| 2020-12-17 |  |  |  |  | Monday morning demo
| 2020-12-24 |  |  | Create micro website
| 2020-12-31 |  |  |  |  | Monday morning demo
Q2 CI/CD | 2021-01-07 | Continues Integration Continuous Delivery | Setup Azure Cloud Shell
| 2021-01-14 |  |  |  |  | Monday morning demo
| 2021-01-21 |  | Create GitHub Action
| 2021-01-28 |  |  |  |  | Monday morning demo
| 2021-02-04 |  | Setup Azure pipeline
| 2021-02-11 |  |  |  |  | Monday morning demo
| 2021-02-18 |  | Build Azure pipeline
| 2021-02-25 |  |  |  |  | Monday morning demo
| 2021-03-04 |  | Run ML microservice
| 2021-03-11 |  |  |  |  | Monday morning demo
| 2021-03-18 |  | Create Alert
| 2021-03-25 |  |  |  |  | Monday morning demo
Q3 Quality Assurance Testing | 2021-04-01 | Create automated tests | Pytest test
| 2021-04-08 |  |  |  |  | Monday morning demo
| 2021-04-15 |  | Integrate pytest test into makefile
| 2021-04-22 |  |  |  |  | Monday morning demo
| 2021-04-29 |  |  |  | Write locust tests
| 2021-05-06 |  |  |  |  | Monday morning demo
| 2021-05-13 | Validate results and performance |  |  | Run locust tests, evaluate results
| 2021-05-20 |  |  |  |  | Monday morning demo
| 2021-05-27 |  | Validate GitHub action
| 2021-06-03 |  |  |  |  | Monday morning demo
| 2021-06-10 |  | Validate Azure pipeline
| 2021-06-17 |  |  |  |  | Monday morning demo
2021-06-24
Q4 Documentation | 2021-07-01 | Create video | Capture videos of the backend and frontend development
| 2021-07-08 |  |  |  |  | Monday morning demo
| 2021-07-15 |  |  |  | Capture local setup and tests videos
| 2021-07-22 |  |  |  |  | Monday morning demo
| 2021-07-29 |  | Video montage and overdub
| 2021-08-05 |  |  |  |  | Monday morning demo
| 2021-08-12 | Write readme.md |  |  | Create architectural diagram
| 2021-08-19 |  |  |  |  | Monday morning demo
| 2021-08-26 |  |  |  | Document installation and deployment process
| 2021-09-02 |  |  |  |  | Monday morning demo
| 2021-09-09 |  |  |  | Document testing and how to use the API
| 2021-09-16 |  |  |  |  | Monday morning demo
| 2021-09-23 | Deploy | Deploy
|  |  | Goals | Goals
|  |  | ML API | Deployed on Azure
|  |  | Logging | Angular
|  |  | Continuous integration | Setup github
|  |  | Continuous delivery | Setup azure pipelines
|  |  | Documentation | Create video and readme.md
| Difficulty | Estimated time
| Easy | May need up to 25% less time than estimated
| Medium | Expected to meet the xpected timeframe
| Hard | If an unexpected incompatibility or bug is raised, it may need up to 25% more time than estimated.