## Project Management Plan
Week | Backend | Frontend | Local | Demo
2020-10-01 | Build system | Build system
2020-10-08 | Continues integration | Continues integration |  | Monday morning demo
2020-10-15 | ML API | ML API
2020-10-22 | Continues integration | Continues integration |  | Monday morning demo
2020-10-29 | Test with github action | Test with github action
2020-11-05 | Continuous delivery | Continuous delivery |  | Monday morning demo
2020-11-12 | Test and deploy with azure pipelines | Test and deploy with azure pipelines
2020-11-19 | Backend ready for QA | Frontend ready for QA |  | Monday morning demo
2020-11-26 |  |  | Write and run pytest test
2020-12-03 |  |  | Locust tests | Monday morning demo
2020-12-10 |  |  | Create video
2020-12-17 |  |  | Write readme.md | Monday morning demo
| Goals | Goals
| ML API | Deployed on Azure
| Logging | Angular
| Continuous integration | Setup github
| Continuous delivery | Setup azure pipelines
Difficulty
Easy
Medium
Hard